## Sheet1
Note to self, update the ending date for the chart when our presentation date is assigned
Project began on 01/15
Task | Start Date | Days Taken
Set up server & domain (Sami) | 2021-01-15 | 1
Set up home page (Craig) | 2021-01-17 | 1
Set up database and tables (Brian) | 2021-01-18 | 1
Made ERD, use case diagram, Gantt Chart template (Brian) | 2021-01-19 | 1
Designed PowerPoint to house previous documents (Brian) | 2021-01-19 | 1
Designed a Main Page for the website to use(Craig) | 2021-01-24 | 1